## Defects
SI No. | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Harini T | 2026-02-16 | User login fails for new users | Milestone 1 (Weeks 1–2) | Self | Logical | Implemented Firebase authentication and validated input fields | 2026-02-16 | Closed | Login now works for all registered users
2 | Harini T | 2026-02-28 | Cold-start users get irrelevant recommendations | Milestone 2 (Weeks 3–4) | Self | Logical | Added fallback recommendations for new users based on top-rated products | 2026-02-28 | Closed | Recommendations are meaningful for new users
3 | Harini T | 2026-03-14 | Duplicate or repeated products in recommendation list | Milestone 3 (Weeks 5–6) | Self | Maintainability | Added filtering logic to remove duplicates in product recommendations | 2026-03-14 | Closed | Product list displays unique recommendations
4 | Harini T | 2026-03-28 | Login page and frontend display slow for large product list | Milestone 4 (Weeks 7–8) | Self | Standards | Optimized React rendering and caching; improved API calls | 2026-03-28 | Closed | Page loads faster; frontend shows recommendations correctly

## Sheet2
Logical
User Interface
Maintainability
Standards
Others